## Unit Test Cases
Project Name: | IDVS |  |  | Prepared By | Mujeeba Zainab Khan |  |  |  | Reviewed By | Rajashekarreddy Kasireddy
Project ID: | Malaysia Airlines |  |  | Prepared Date | 2022-08-05 |  |  |  | Reviewed Date
Test Type: | Unit Testing
CR No | Description |  |  | PASS | FAIL | N/A | NOT STARTED | TOTAL | % PROGRESS
CHG0023147 | IDVS and FY AD integration |  |  | 7 | 0 | 0 | 0 | 7
(Pass/Fail/NA/Not Started)
S.No | Module Name | Pre-Condition | Input Data | Boundary Value Analysis(YES/NO) | Defect ID | Severity (H/M/L) | Test Status | UI/Functionality | Tested by | Date of execution | Test Case ID | Test Description | Test Steps | Test Iterations | Test Data | Expected Result | Actual Result | Test Browser | Tested by | Comments
1 | Login | User should have proper access to the application. | User needs to enter username and password in IDVS app. | NO |  | H | Pass |  | Mujeeba Zainab Khan | 2022-08-05 | 1 | Login functionality test | 1. Login | 1 |  | User should be able to see the landing page in browser |  | Chrome | Mujeeba Zainab Khan | NONE
2 | Create User | User should have proper access to the application. | Staffid ********* | NO |  | H | Pass |  | Mujeeba Zainab Khan | 2022-08-05 | 2 | If userId already exists in AD |  | 1 |  | User information should be present in IDVS with status - Active/Inactive |  | Chrome | Mujeeba Zainab Khan | NONE
3 | Create User | User should have proper access to the application. | Staffid ********* | NO |  | H | Pass |  | Mujeeba Zainab Khan |  | 3 | If userId does not exist in AD |  | 1 |  | Create a new user with new email and password, setting the status as Active and all attributes will be added in AD. |  | Chrome | Mujeeba Zainab Khan | NONE
4 | Modify User details | User should have proper access to the application. | Staffid ********* | NO |  | H | Pass |  | Mujeeba Zainab Khan |  | 4 | UserId exists in AD and if manager info is null. |  | 1 |  | 15 attributes of a user can be modified. |  | Chrome | Mujeeba Zainab Khan | NONE
5 | Modify User details | User should have proper access to the application. | Staffid ********* | NO |  | H | Pass |  | Mujeeba Zainab Khan |  | 5 | UserId exists in AD and if manager info is not null. |  | 1 |  | 16 attributes of a user can be modified (manager will be the extra one) |  | Chrome | Mujeeba Zainab Khan | NONE
6 | Modify User | User should have proper access to the application. | Staffid ********* | NO |  | H | Pass |  | Mujeeba Zainab Khan |  | 6 | UserId exists in AD and if it has to be moved. |  | 1 |  | Changing the OU details, User get enabled. |  | Chrome | Mujeeba Zainab Khan | NONE
7 | Disable User | User should have proper access to the application. | Staffid ********* | NO |  | H | Pass |  | Mujeeba Zainab Khan |  | 7 | UserId exists in AD and if it has to be removed/disabled. |  | 1 |  |  |  | Chrome | Mujeeba Zainab Khan | NONE

## System Test Cases
Project Name: |  |  |  | Prepared By |  |  |  |  | Reviewed By
Project ID: |  |  |  | Prepared Date |  |  |  |  | Reviewed Date
Test Type: | Systems Integration Test
CR No | Description |  |  | PASS | FAIL | N/A | NOT STARTED | TOTAL | % PROGRESS
(Pass/Fail/NA/Not Started)
S.No | Test Scenarios | Module Name | Application Version No. | Build No. | Application URL | Pre-Condition | Defect Id | Test Case ID | Test Case Iterations | Test | Test Description | Test Steps | Test Data | Expected Result | Actual Result | Test Status | UI/Functionality | Tested by | Date of execution | Comments
1 | MHM should display a landing page containing Aircraft status icon. | Login | 5.2 | 5.2 | https://mhmessenger.malaysiaairlines.com/mhmessenger/ |  |  | 1 | 1 | Login functionality test | Login functionality test | User needs to enter username and password in Mobile app. | Staffid ********* | User should be able see Landing page in mobile |  | PASS | Y | Mujeeba Zainab Khan | 2022-06-01 | NONE